## consolidated
10 June 2016 Country | ID | Topic | ITP action | Main deliverable (as per ITP proposal) | Detailed activities (as per ITP & TS workplans) | TA request | Update on technical support | Comments | FP
Angola | NI | SI |  |  | NT Capacity building and M&E tools validation 1- Int. Consultant 2. NPO recruitement |  |  |  | Txema
Angola | NI | Toxicity monitoring |  |  | ARV : Pharmaco vigilance |  |  |  | Francoise
Angola | NI | ART |  |  | Peads TOT |  |  |  | Marco
Angola | NI | Key Pops |  |  | Capacity building national team to work with the Key Pop. (counseling and prevention based on Human Rights) |  |  |  | Carmen
Benin | 156 | ITP action | Workshop in Cotonou on Jan/Feb 2016 with Partner support to define how to reinforce the National Quantification Committee to ensure accurate quantification of HIV health products | Workshop completed with clear recommendations on how to reinforce National Quantification Committee and technical support provided for more accurate quantification of HIV health products | Organiser un atelier sur le rôle de la CAME dans la chaîne d'approvisionnement des médicaments au Bénin Recruter un personnel d'appui pour la mise en œuvre des actions ITP Elaborer et valider les termes de références du consultant GAS ARV et réactifs Elaborer et faire approuver le MoU entre PNLS et l'OMS Recruter un consultant GAS ARV et réactifs pour une durée d'un an sur finacement du Fonds Mondial Organiser une réunion avec la partie nationale pour élaborer un plan de renforcement de capacités du CNAPS (Comité National d'Approvisionnement des Produits de Santé) Organiser un atelier de renforcement des capacités des membres du CNAPS Organiser les sessions trimestrielles des sous-comités VIH/Sida, Paludisme et Tuberculose du CNAPS Organiser les sessions semestrielles du CNAPS | WCO is waiting for a request to recruit an int'l PSM consultant for one year. The request is supposed to come form CCM via the GF. Télésphore is following up with Vincent |  |  | Vincent
Botswana | NI | Testing |  |  | Botswana intends to soon adopt the Treat All strategy as per WHO recommendations, which requires that the country puts in place strategies to have universal HIV testing and ensure that all Botswana know their HIV status and can therefore access prevention, treatment, care and support services. This Necessitates the conduct of a comprehensive HTS programme review to inform HTC strategies for universal HTC services. KPP to provide a consultant to work on HTS review with funding from SIP. APW ready through AFRO | APW being prepared by AFRO to Annrita Njeri Ikahu | SIP provided seed funding for the HTS review. KPP recommended two consultants from LVCT health Kenya to lead the review. How much 23 000?? HQ to discuss with the Global Fund on financing the complete review agenda?? |  | Cheryl
Botswana | NI | ART |  | Finalisation of dialogue on implementation modalities and logistics on Treat all ( “Test n Treat”) | HQ(TAC) will also provide Treat All implementation/advocay briefs when they become available.
Botswana | NI | PSM |  | Finalise the draft 2015 guidelines | HQ will support development of procurement plan for Treat All.
Botswana | NI | PMTCT |  | eMCTC validation | HQ (TAC), RO, IST will provide a consultant to work on the pre-validation roadmap (tbc). The consultant could also work on defining the PMTCT and STI parts of the HIV programme review.
Botswana | NI | Key populations |  | Support BBSS 2 (KP Mapping) | HQ(SIP) will provide a consultant. HQ will also provide new BBS tools, with guidelines and questionnaires, which will be available mid-2016.
Botswana | NI | Key populations |  | KP focused testing Interventions included in the NSP revision, and revision of the HTS guidelines | HQ/RO will provide remote support in reviewing draft guidelines. IST to provide more direct support
Botswana | NI | Prevention |  | Site readiness assessments and training Healthcare workers for scaling up Early Infant Male Circumcision in 2 more hospitals in 2 districts, with supported HCW trainings | TA for training (IST) and funding (HQ) in April/May
Burkina Faso | 102 | ITP action | The assessment of the current unique identifiers systems in place and initiation of a simplified/harmonized identification system (unique identifier code) for key population and people living with HIV, taking stock of current challenges. // L'évaluation des systèmes actuels d'identifiants uniques en place et le lancement d'un système simplifié / harmonisé identification (code d'identification unique) pour la population clé et les personnes vivant avec le VIH, faire le point sur les défis actuels / | Assessment report of the current unique identifier systems finalised and adopted with recommendations for a simplified system for key population and people living with HIV | Appuyer la réunion d'élaboration/validation des TDR en collaboration avec Le PSSLS-IST, IPC et Le SPCNLS-IST Organiser une mission de 10 jours pour L'évaluation des systèmes actuels d'identifiants uniques en place avec un consultant international Organiser un atelier national de validation national du système simplifié d'identification unique en 03 jours organiser un atelier national d'adaptation des outils au système simplifié d'identification unique en 03 jours | Request on 27 May, from AFRO for a francophone consultant, 25 days. The WCO need 3 CVs to choose from. | HQ sent to AFRO 3 CVs (Schumacher, Mathers, Mulot) these with the CV of Zougouri were sent to WCO for review. A national consultant is also needed. The country accepted Mathers and Schumacher. Mission is planned for 25 July. Also a national consultant (Simpore) was selected.
Cameroon | 59 | ITP action | Partner advocacy for strengthening of CNLS (MOH to fill all vacant positions before start of NFM program implementation) | Technical support with mechanisms for regular monitoring visits and workshop by the WHO Country Office (WCO) to HIV sub Directorate in MOH to strengthen CNLS programme management at national and regional level. | Staff cost of HIV program Officer (NOC) to support implementation of ITPs actions and provided TA to the HIV sub-Directorate in the MoH for advocacy in programme management In-country Travel (for local staff): The project technical advisor and one driver (for 45 days field trip) to support activities
Cameroon | 60 | ITP action | Additional technical support to NACC, especially for program management, may be required (e.g. one-year embedded advisor) | Three national technical assistants recruited to facilitate implementation of Test and Treat All Strategy and monthly technical reports on increase ART scale up done, and operational document on Test and Treat All developed and national HIV testing policy revised | Recruit 03 national technical assistants (SSA, Grade NOA) for 6 months to support the implementation of ART Scale-up through mentoring of staff in ART units in 6 regions (Adamanoua, East, Far-north) Ensure transportation and communication facilities for the activities of the 3 "scale-up team" Recruit national consultant to support the elaboration of the operational document to facilitate the implementation of the "Test and Treat" all strategy HIV including the revision of national HIV testing policy Support the organisation of 1 workshop to validate the operational document to implement "Test and Treat" all HIV including revision of national HIV testing policy | Request from AFRO for technical and financial support to develop an operational document on implementation of Treat All strategy. Need an international expert, national consultant and catalytic funding. | Meg is following up. two reminders received from Nirna asking about the intrnational expert. AFRO still waiting for a response from HQ. Meg contacted MSF for input, but the STCs contacted by MSF are not available. Vincent contacted Charabi for his availability. Kemal Cherabi confirmed his availbility for support. The national consultant is almost selected. | Meg is FP
Cameroon | 71 | ITP action | Partner with World Bank, GAVI, UNICEF and other stakeholders to build integrated community component and to consider implementation of PBF by mid-2016. | Validated integrated strategy for community activities and 57 community health workers trained to implement integrated activities for HIV, TB and malaria | Support the organization of a national workshop to validate the integrated strategy for community acivities document Translate into english, Print and disseminate the integrated strategy for community activities Support the training of 57 Community health workers (including Key Population groups) from selected districts on the implementation of integrated community services for HIV, TB and malaria
Cameroon | NI | SI |  |  |  | Request for technical and financial support for the training workshop on the realization of the analysis of HIV cascade (PMTCT, PrEP, and ART) in Cameroon. | $13,558 sent by SIP to support cascade workshop.
Cameroon | NI | ART |  | Treat All: Accelerate ART: - Advocacy to strengthen capacities of NACC (at national and regional levels) including TA for program implementation - Support rapid scale-up of tasks shifting/mentoring for PMTCT/ART and Paediatric care - Community dispensation of ARV. | HQ will provide Treat All advocay materials and implementation guides.
Cameroon | NI | Testing |  | Advocacy for the revision of national policy to include community testing, lowering aged for adolescents/youth testing | IST/RO and HQ to advise on algorithms for re-testing and managing pre-ART.
Cameroon | NI | PMTCT |  | Support rapid scale-up of tasks shifting/mentoring for PMTCT/ART and Paediatric care | Joint mission of HQ and AFRO in Q3 to support the National Forum. RO/IST to support national consultant to document best practices. HQ to provide simple available assessment tools. Aslo to be invited to the AFRO workshop on B+.
Cameroon | NI | SI |  | Training of M&E staffs on cascade monitoring Implement cohort analysis for PMTCT and ART | HQ to provide training tools and share the new case reorting and patient monitoring tools.
Cameroon | NI | ART
Chad | 253 | ITP action | Training health professionals involved in supply chain (at PR, SR, district level) on quantification, inventory management and stock monitoring | Five trainings for health professionals in supply chain conducted | Organiser 5 sessions de formation sur la chaine d'approvisionnement, l'estimation, la gestion des inventaires, et le suivi des stocks à l'intention des gestionnaires de stock au niveau des PR, des SR, des hôpitaux et des districts |  | TC on 26 May with HIV, HSS, EMP, IST and WCO to discuss techical support. WCO will send a revised support plan on 27 May. WCO to send a revised plan based on discussions. Mayada and Diane will contact Expertise France to explore additional funding possibility. TC on 3 June with WCO and IST to discuss plnaning of ITP activities and possible request of PSM consultant. TC on 10 June to review ITP planned activities, a NFR is available. WCO has been requested to send the timetable of different tasks. | WCO sent detailed ITP plan 2 June | Mayada
Chad | 316 | ITP action | Technical support (12 months) for detailed assessment of current situation, design and development of LMIS and required tools, and support in implementation | Detailed assessment of LMIS current situation completed with clear recommendations on design, structure and mechanisms, and tools and support needed in the implementation phase. | Fournir l'appui technique par 6 consultants pour les sous bureaux OMS pour l'appui à la chaine d'approvisionnement Appuyer les missions de supervision des consultants pour l'appui à la gestion des stocks au niveau des districts Fournir les équipements, outils informatiques et matériels de communication pour les consultants Financer les frais de communication liés à la collecte des données sur les stocks et les consommations Acquérir 6 motos pour les activités de surpervision des 6 consultants en appui aux sous Bureaux OMS Assurer les frais de carburant et de maintenance des 6 motos |  |  | WCO sent detailed ITP plan 2 June | Mayada
Chad | 257 | ITP action | Technical support for development of community health strategy and operational plans for community interventions for each disease component |  | Fournir au MSP (DOSS) l'appui technique par un consultant national pour le dé veloppement des activités communautaires de chacune des 3 maladies dans le cadre du Plan startégqiue de santé communautiare (Ref. activité N°64 du Plan stratégique de santé communautaire) Effectuer des missions de terrain pour l'appui à la formation des formateurs sur les module de fomation des ASC et sur les techniques de facilitation (Ref. activité N°10 du Plan stratégique de santé communautaire) Fournir l'appui technique aux MSP et PTF impliqués dans l'ITP pourles réunions d'élaboration des plans opérationnels annuels de mise en œuvre de chacune des stratégies communautaires prioritaires (PCIME communautaire, PECADOM, et PTME communautaire).(Ref. activité N° 27 du Plan stratégique de santé communautaire) Acquérir des équipements informatiques et supports de communication |  |  | WCO sent detailed ITP plan 2 June | Mayada
Chad | 258 | ITP action | Need to support the improvement of the collaboration amongst CCM, PRs, MOH as well as with national programs | Strengthened collaboration among CCM, PRs, MOH and national programs through regular consultation meetings on the implementation of the Action Plan and on progress in implementation of Global Fund grants, and regular information products disseminated | Fournir l'appui technique par un consultant national pour la coordinantion centrale des activités ITP y compris les 6 consultants GAS Organiser des rencontres de concertation OMS avec le MSP (UTC) surla mise en œuvre du Plan d'action de l'UTC et les progrès dans la mise en œuvre des subventions Fonds mondial par les programmes nationaux (sous-recipiendaires) Organiser des réunions de concertation entre PTF et CCM/HCNC Diffuser aux PTF et aux autres acteurs les informations relatives aux subventions Fonds mondial, grâce à la participation du CCM (HCNC) et des PR aux rencontres mensuelles de concertation des PTF et au soutien à l'élaboration de brochures d'information par le HCNC et les PR Fournir l'appui technique au MSP par un consultant web master pour le renforcement du site web du MSP en vue de la diffusion des données liées aux activités ITP/Fonds mondial Fournir les équipements, outils informatiques et matériels de communication pour un consultant au niveau central Financer les frais de communication liés à la coordination au niveau central |  |  | WCO sent detailed ITP plan 2 June | Mayada
Côte d'Ivoire | 321 | ITP action | Engage a consultant to develop the national M&E Plan as part of the National Strategic Plan | National M&E plan for the NSP finalised | Soutenir le MSHP pour l’organisation des réunions du groupe de travail Fournir au MSHP l’appui technique par un consultant national en soutien au groupe de travail d’élaboration du plan de suivi et évaluation (20 jours) Fournir l’assistance technique d’un expert en Suivi et évaluation pour faciliter le développement du plan de suivi évaluation du Plan stratégique National de lutte contre le VIH 2016-2020 (15 jours) Soutenir l’organisation des ateliers d’élaboration et de validation du plan de suivi et évaluation du PSN VIH soutenir l’organisation d’un atelier de renforcement des capacités sur l’analyse de la cascade des soins VIH Apporter un appui logistique aux activités | TA for M&E consultant TA for NSP validation | a sum of XXX USD was provided??? Vincent assisted in the NSP valiation process. Requested also a peer review of the draft but no one did from HQ except Vincent. Daniel Tarantola provided support 11-26 May. He is also following up with remote TA. In principle a mission may be planned in July??!
Côte d'Ivoire | NI | SI |  | Cascade analysis and strengthening M&E | HQ to provide a consultant on cascade analysis and UI | WCO need a STC for that, they will let us know in due course
Côte d'Ivoire | NI | Key populations |  | Estimation de la taille des populations clé (PS-MSM) | HQ to provide the tools. RO and IST to assist in translation where necessary
Côte d'Ivoire | NI | ART |  | Mission de plaidoyer - Treat All | HQ, RO and IST to consider participating in advocacy mission
Côte d'Ivoire | NI | Key populations |  | Révision du paquet de services | Echanges avec les autres parties prenantes au niveau national prévu à Q1 pour confirmer les besoins spécifiques
Côte d'Ivoire | NI | Prevention |  | Estimation du Cout de la prophylaxie préexposition
Côte d'Ivoire | NI | Testing |  | Mise à jour des documents de politiques et directives | HQ, RO, IST to peer review the draft documents
Côte d'Ivoire | NI | Planning |  |  |  |  | HQ participation in the validation process of new HIV NSP 15 to 18 March 2016.
DRC | 286 | ITP action | Provision of seconded advisors (one for HIV and one for TB) to provide daily follow-up on quantifications, stock management, orders and especially all international orders made from the DRC | Seconded WCO staff to MoH provided for nine months to conduct daily follow up on quantifications, stock management, and orders for HIV. Please note additional technical support will be provided for TB).C18 | Assurer le suivi de toutes les acquisitions VIH au pays (ARV-tests). After discussion with USG, WHO and GF, the ITP action 286 is being split into 2 actions: - one for an HIV adviser - WHO to be focal point/sponsor on that - one for a TB adviser – USG/USAID to be focal point/sponsor on that |  | joint mission to take place the week of 6 June, about VL/EID scale-up implementation plan. Jean-Bosco Lab AFRO will participate. Other partners include GF (Bruno Viana and Martine Guillerm), Contantin Kabwe (CDC lab)
DRC | 289 | ITP action | Improve MoH PR Capacity in project Management through seconded advisor | Strengthened MOH PR capacity in project management through collaboration between international staff provided by France Expertise and the national staff of the WCO who is familiar with DRC on structures and processes, and completed monitoring and implementation missions to sub-recipients in regions and districts | Concertation PR&PTF&PNLS
DRC | NI | Planning |  | HIV NSP for health sector | HQ will review the draft plan remotely and provide feedback. IST/RO will participate in in-country validation (joint assessment) of the strategic plan.
DRC | NI | PMTCT |  | Management of DBS transportation | Need a consultant to assess lab capacity in the country
DRC | NI | PMTCT |  | HIV and syphilis MTCT Elimination follow-up by provinces | HQ to consider providing funding. Look into possibility of ITP/PEPFAR support.
DRC | NI | ART |  | Preliminary thinking about guidelines revision | HQ to make available costing tool.
DRC | NI | SI |  | 90-90-90 cascade follow-up by provinces
DRC | NI | SI |  | Software Tier.net scaled-up
DRC | NI | Key populations |  | Key pop assessment done in 44 cities in DRC | HQ (KPP) to consider supporting a consultant.
Ethiopia | NI | ART |  | Advocate and support the revision the national HIV guidelines, training materials and other tools in line with treat - all | HQ to consider providing consultant on costing and advocay materials and tools for Treat All. Support expected in Q2.
Ethiopia | NI | SI |  | Support FHAPCO in the development of the national strategic information/M&E framework along the HIV cascade and Hepatitis Support EPHI in the transition from ANC based surveillance to PMTCT routine program data based surveillance | HQ/RO/IST to consider providing staff or consultant to support national and sub-national cascade analysis | TA to support MoH to conduct assessment of national HIV surveillance system | Txema went on mission the week of 16-20 March
Ethiopia | NI | SI |  | Support FMoH in the inclusion of key indicators in HMIS which will be used for monitoring of HIV prevention, care and treatment among key population | HQ, RO and IST to review the draft M&E framework and provide comments , March
Ghana | 177 | ITP action | Review attribution of ART among GHS, GF, other sources in light of 90-90-90 targets |  | Finalization of the NSP and other key policies Advocate for treat All approach Convene stakeholders' meeting | Request from NACP & WCO to review final proposal application | Eyerus and Mazuwa reviewed the proposal and sent feedback to WCO. |  | Mazuwa
Ghana | NI | ART |  | Improved access to quality ART and testing services in general population towards 90 90 90 targets | Improved access to quality ART and testing services in general population towards 90 90 90 targets
Ghana | NI | ART |  | TB/HIV collaboration | TB/HIV collaboration
Ghana | NI | SI |  | M&E bulletin | M&E bulletin
Ghana | NI | Testing |  | HIV testing services | HIV testing services
Ghana | NI | ART |  | Improved utilization of EID services and Pediatric HIV treatment, care and support | Improved utilization of EID services and Pediatric HIV treatment, care and support
Ghana | NI | ART |  | HIVDR | HIVDR
Ghana | NI | ART |  | Treatment |  | Development of a national roadmap (scale up plan) towards Treat All and 90 90 90, to be used in funding request to PEPFAR. | Draft submission to PEPFAR and other documents were shared. These were reviewed and comments for improvement sent.
Guinee | 118 | ITP action | Deploy Surge Capacity Team to support launch HIV scale up and support grant activities immediately while CNLS is building its capacity and “catching up” |  | Assurer l'appui technique à la mise à échelle des interventions de riposte VIH subventionnées par le Fonds mondial
Guinee | 120 | ITP action | Support strengthening of HIV laboratory network by 1) short term technical support to assess services, needs and develop plan and 2) long term support to implement changes |  | Recruter un consultant international pour l'évaluation du réseau de laboratoire du VIH Evaluer le résaeu de laboratoire VIH Elaborer un plan de renforcement du résau de laboratoire VIH Apporter un soutien à long terme pour mise en œuvre du plan de renforcement du laboratoire VIH (done by expertise Francaise)
India | 9 | ITP action | Advocate for implementation of the midterm review for HIV program to feed into the development of the next NSP | Technical Support provided for the implementation and completion of the mid-term review (MTR) for the HIV program. |  | Request to HQ for participation in the debriefing meeting of programme review. WHO: "Mid term review planned for June with support from WHO and partners" | Mazuwa will participate. Also Gottfried and Stefan are going to country on world Hep day.
Kenya | 323 | ITP action | Assessment of resources needed for DHIS 2 expansion to the facility level | DHIS2 assessment of resources needed to expand to facility level completed | Recruitment of consultants (2) to conduct the assessment Stakeholder meeting to discuss the inception report and assessment tools Conduct of the assessement, including field visits (including travel for MOH participants) Stakeholder meetings (x2) to discuss the assessment findings and validation Printing and dissemination of the assessment report |  | Ties team in collaboration with SIP is organizing a joint mission to Kenya
Kenya | 49 | ITP action | Resources needed for the DHIS 2 expansion contractors, soft / hardware and start-up training costs should be mobilized from partners / donors. (SPLIT NEW ACTION FROM 49: Support Kenya enable facilities that have EMR to directly report to the DHIS2) | Resource estimation completed for the DHIS 2 expansion contractors, soft/hardware and start-up training cost | Develop concept note and TORs to suppport development of interoperability platform between DHIS2 and HIV Treatment Electronic Medical Records (EMRs) systems developed by different partners Recruit a consultant based in NASCOP to develop the interoperability platform between DHIS2 and EMRs, and support capacity building on data demand and use at sub-national level TWG retreat to discuss the consultant's inception report on the interoperability platform Stakeholder meetings (2) to discuss the draft interoperability platform and finalize it Develop an implementation plan for phase 1 of the interoperability platform roll out in 50 selected high volume facilities covering the main EMRs systems in use in the country Roll out phase 1 of the interoperability system to 50 high volume selected facilities Document experiences in the roll out of the system in 50 high volume selected facilities Stakeholder meeting to discuss the experiences and national scale up plan Develop and validate a resource mobilization plan for national roll out Salary contribution to the WHO HIV Officer Salary for project coordination | Request for consultant??? | John Cutler going to Kenya jointly with HIS (Ties team)????
Kenya | NI | ART |  | Adaptation of Treat All guidelines and capacity building - TOTs - for their implementation | HQ and RO to support with a consultant for the guidelines. HQ/RO/IST will be available to review the draft guidelines. HQ to provide information on evidence for the guidelines.
Kenya | NI | SI |  | Revised M&E data collection and analysis tools National ART cohort analysis report that contributes to GARPR Health sector HIV program review conducted | HQ support provided through consultant
Kenya | NI | Planning |  | HTC program review conducted | WCO to confirm details of HIV program review and type of support required from IST, RO, HQ
Kenya | NI | PMTCT |  | Support eMTCT Stock taking meetings at county and national levels. | The country will develop concept note and TORs than come back to RO/HQ
Kenya | NI | PMTCT |  | Preparatory work for elimination validation | The country will develop concept note and TORs than come back to RO/HQ
Kenya | NI | VMMC |  | Medical devices surveillance for adverse events conducted and reported on | HQ/IST to provide assessment tools
Kenya | NI | VMMC |  | VMMC impact assessment supported | HQ/IST to provide tools for impact assessment
Kenya | NI | ART |  |  |  | Requesting CVs of potential international consultants for development of the ART Guidelines in line with the 2015 WHO recommendations.
Lesotho | NI | PMTCT | Review emtct Plan including evaluation |  | Country office- Develop a concept note and TORs for WHO TA support
Lesotho | NI | Testing | Adaptation of HTS guidelines |  | In country processes started and HQ/RO provide peer review of the draft documents
Lesotho | NI | Prevention | National VMMC Operation Plan |  | Country office- Develop a note and TORs for WHO TA support
Lesotho | NI | ART | National ART scale up plan including cascade analysis |  | Country office- Develop a note and TORs for WHO TA support
Lesotho | NI | ART | Dissemination/adoption of the WHO 2015 ARV Guidelines |  | WHO- RO/HQ will preovide peer review of the National adopted guidelines
Lesotho | NI | ART | Review of National ARV Guidelines and other related tools |  | Country office- Develop a note and TORs for WHO TA support
Liberia | NI | PSM |  |  |  | Request came through GTB and the GF (7 June) for for a PSM consultant | GTB will organize a TC with IST and Cornelia (TB FP for Liberia, Sierraleone and Guinea), Vincent and GTB to discuss the TA
Malawi | 326 | ITP action | Operational Program Implementation Unit (PIU): Mobilize embedded 6 – 12 months technical support individual | M&E consultant for 6 months recruited to strengthen M&E systems and mechanisms for the PR and national staff capacity built. | Operational Program Implementation Unit (PIU): Mobilize embedded 6 – 12 months technical support individual .
Malawi | 76 | ITP action | Partners to support PRs for operationalization of HIV prevention among key populations, young women, girls and VMMC including development of a detailed work plan for implementation of priority program areas, and establishment of joint mechanisms to track progress on a periodic basis |  |  |  | 17 May: WCO is waiting for feedback from the DIrector of HIV in MoH. |  | Julie
Malawi | NI | SI |  | Tools adaptation | The document is being prepared at Country level. It will be shared to HQ and RO/IST for peers review. HQ indicated to have seed funds to kick start some SI activities
Malawi | NI | ART |  | Treatment guidelines/delivery models | IST/RO/HQ to review the drft guidelines. HQ to assist in developing training curriculum.
Malawi | NI | Prevention |  | EIMC guidelines adaptation | IST to provide guidelines of Tanzania
Malawi | NI | Testing |  | Fast tracking HIV testing services including piloting self-testing | IST/RO/HQ to review the drft guidelines. IST to support seting up of pilots for self testing
Malawi | NI | PMTCT |  | Pre-elimination
Mali | 260 | ITP action | Support the development and review of a laboratory plan for scale up of patient monitoring |  | Repertorier les laboratoires existants offrant le suivi biologique du patient VIH Identifier les besoins en laboratoire pour le suivi des patients VIH Atelier d'élaboration du plan d'extension des laboratoires pour le suivi des patients VIH Atelier de validation du plan d'extension Mse en place d'une assurance-qualité pour les réseaux de laboratoire recyclage du personnel du réseau de labo renforcer le plateau technique des laboratoires existants en fonction des besoins identifiés
Mali | 264 | ITP action | Develop detailed operational plan for PMTCT scale-up, including for EID and transition to option B+ . TA to be requested during December visit |  | Atelier de finalisation du plan opérationnel d'extension de la PTME option B+ Atelier de validation du plan opérationnel Dissémination du plan opérationnel Organisation du forum des partenaires pour la mobilisation des ressources recrutement d'un consultant national pour l'élaboration des référentiels pour la délégation de taches atelier de finalisation des référentiels pour la délégation de taches atelier de formation des formateurs surla délégation des taches aux paramédicaux ateliers de formation en cascade appuyer le MSHP pour la mise en place des intrants au niveau Cscom Multiplication des référentiels pour la délégation des taches aux paramédicaux
Mozambique | NI | SI |  |  |  | Request for country experiences in developing M&E tools including paper register, age/sex disaggregation cohort analysis and identification of deaths and loss to follow up. |  |  | Marco
Mozambique | NI | SI |  | Revised ART M&E tools: Ongoing process. WHO- part of the WG to assure alignment with the Consolidated Strategic Information Guidelines (May 2015) and integration with national surveillance and M&E systems | The process had started and a consultant is on ground and a working group established. Will send the updated tool for peers review
Mozambique | NI | Testing |  | Guidelines for integrated HTS | The guidelines have been updated and endorsed by the Government in Jnuary 2016. It will be shared and comments provided
Mozambique | NI | Prevention |  | VMC National Strategic Plan (2013-17) review | Both technical and Financial assistance are required. WCO will update after discussion with MOH
Mozambique | NI | PMTCT |  | Support MoH in evaluating the feasibility of introducing early male circumcision | National strategic plan for fast tracking dual elimination of MTCT of HIV and congenital syphilis | MOH is keen on doing a rapid evaluation of their PMTCT programme with a view to formulating a strategic plan for the next 5 years to address any programme shortcomings
Mozambique | NI | ART |  | Disseminated global guidelines + developed national adaptation roadmap and piloting a step-by-step approach to implementing Treat All | Marco Vitoria will visit the country next week and will advise
Mozambique | NI | ART |  |  |  | Requesting technical and financial support to develop an operational document on implementation of Treat All strategy. Need an international expert, national consultant and catalytic funding. | TAC sent Marco to attend the national guidelines meeting and identify, in consultation with WCO and MOH, key areas for WHO technical support to Mozambique.
Myanmar | NI | Planning |  |  |  | Request to review of draft Concept Note (8 June) | on 8 June, Mazuwa sent the documents to a selection of HQ staff for review
Niger | 168 | ITP action | Technical support to develop an operational plan for scale-up of ART and PMTCT to be developed / technical support needed immediately (Nov 2015) (Highest priority) |  | Finalisation du draft de plan d'extension en prenant en compte les nouvelles recommandations de l'OMS: Test and treat Organiser un atelier de validation du plan finalisé Reproduire le plan final en 1000 exemplaire Organiser 8 ateliers regionnaux de vulgarisation du plan validé | AFRO shared a CCM request on 3 June asking for financial support.
Niger | NI | PSM |  |  | a GF mission of went to Niger 6 June. They will meet the WR and NPO.
Nigeria | 190 | ITP action | Support the development of an implementation plan that supports integration of services and mobilization of community engagement component within national primary healthcare system
Nigeria | 192 | ITP action | Partner support to conduct joint collaborative review exercise to set nationally agreed co-infection rate. |  | Conduct a desk review on available in-country information; conduct a health facility survey on ICF data among PLHIV; use the information from the 2 reviews to propose co-infection rate of TB among PLHIV; and conduct stakeholders meetings to agree on national co-infection rate of TB among PLHIV
Nigeria | 194 | ITP action | Work with National Lab TWG, WHO CO, NACA, NASCP and USG (PEPFAR/CDC/DOD) to improve the mapping and document public lab network and referral system (to VCT, PMTCT and ART centers) to improve early infant diagnosis |  | Support mapping of ART sites, PMTCT sites and PCR/viral load laboratories Support establishment of facilit-laboratory networks for viral load and EID and allocate each network targets for Dec 2016 Support the established lab networks to develop 6 months operational plan and advocate for its funding
Nigeria | NI | ART |  |  | HQ, RO and IST to participate in the national dissemination conference and provide some financial support about adaptation of ARV guidelines. | Request came on 3 June for TAC particpation 22-24 June. | TAC provided $40,000 to support theworkshop. The plan is to have TAC staff participate. Meg sent an email to Go to discuss HQ TA.
Nigeria | NI | Testing |  |  | HQ to provide a consultant
Nigeria | NI | SI |  |  | HQ to provide consultant and funding for subnational cascade analysis.
Nigeria | NI | SI |  |  | IST to provide consultant
Nigeria | NI | Planning |  |  | Peer review of draft strategy by HQ, IST, RO.
Nigeria | NI | SI |  |  | HQ to consider supporting this effort in conjunction with UNAIDS.
Rwanda | NI | Programme review |  |  |  | Request for WHO consultant or staff to participate in the midterm review of implementation of the NSP. | an amount of USD 18000 was allocated to this activity. Nathan Ford will provide TA.
Sierra Leone | NI | Costing |  |  |  | Request in April for a consultant for the integrated costing analysis of ART (post ebola) | Daniel is contacting a SIP consultant to check her availability
Sierra Leone | NI | GF |  |  |  | Request 9 June from CCM to WHO TA to analyse grant expenditure from 2010 to first quarter of 2016, start date 27 June | On 9 June, Mazuwa sent 3 CVs for considreation by AFRO and WCO
South Africa | 241 | ITP action | Technical support for development of new HIV/TB and STI NSP and National M&E Plan |  | 1 . Consultant in strategic planning - Lead consultant 2. M&E Consultant 3. STI Consultant 4. Consultant for the collation and synthesis of available evidence (domestic and international) 5. External scoping and monitoring mission | Request from WCO for HQ support. Request received end April. Consultants required between May and Nov for NSP, M&E, STI. Cost is 382,000 Request from WCO for TA on analysis the TB and HIV cascades (for Aug 2016) | Regular discussion held with CO and AFRO on the porcess. Two consultants (Brian Williams and Annette Gerritsen) already on board to assist CO with the process. Mazuwa is Focal Point, to coordinate with other teams on their contribution. |  | Mazuwa
South Africa | 243 | ITP action | Support the existing health information system strengthening efforts |  |  |  |  | This should be an ongoing support. HSS team will discuss with Ties to take the lead.
South Africa | NI | Planning |  |  |  | Requesting a total of $382,000 to support the following: 1. Consultant in strategic planning 2. M&E consultant 3. STI consultant Consultant for the collation and synthesis of available evidence. | Two consultant identified: Annette Gerritsen (M&E) and Brian Williams (Knowledge Management). Process of making funds available is underway.
South Africa | NI | ART |  | Support the implementation of HIV treatment Cascade and the 90-90-90 targets for 2020 | WCO will define specific support needed and TORs.
South Africa | NI | ART |  | Advocacy and support the implementation of EWI indicators including follow up | HQ (Silvia) will undertaken an advocacy mission around the time of the dissemination meeting.
South Africa | NI | ART |  | Support guideline development for PrEP and UTT | HQ/RO/IST to provide support in the development and review on guidelines
South Africa | NI | Testing |  | Support quality assurance improvement
South Africa | NI | Testing |  | Support and strengthen linkage to care
South Africa | NI | PMTCT |  | Support pregnancy registry implementation | HQ and IST to provide continued support
South Africa | NI | PMTCT |  | Strengthening PMTCT information management to enhance eMTCT
South Sudan | 293 | ITP action | Technical support for the development of Operation Plan for training of clinical staff | Operational Plan for training of clinical staff developed and endorsed for implementation+C18 | 1. Stakeholder dialogue meetings 2. Revision/update of the operational plan 3. Implementation of the training plan
South Sudan | 294 | ITP action | Technical support for laboratory/diagnostics and quality of services |  | 1. Conduct a comprehensive assessment of Laboratory/diagnostic services 2. Support monthly TWG meetings 3. Support update for lab strategy and operational plan 4. Support development/update of laboratory guidelines and training materials including job aids for HIV ((EID & VL) and TB 5. Support development of system for sample collection, transportation and transmission of results 6. Support establishment of database 7. Update/development of EQA system for lab services
South Sudan | NI | ART |  | Establishing EID | There on going support with WHO HQ for EID and VL introduction and roll out
South Sudan | NI | Testing |  | Support update for national HIV Testing and Counselling strategy, guidelines and training packages | Peer review of draft document
Swaziland | NI | PMTCT |  |  | Development of PMTCT plan
Swaziland | NI | PMTCT |  |  | Pre-validation???
Swaziland | NI | ART |  |  | Cost analysis and implications of new guidelines
Swaziland | NI | SI |  |  | Cascade analysis and training
Swaziland | NI | ART |  |  | routine VL testing and roll-out Situational analysis and laboratory network with capacity assessment for Scale-up plan and decentralisation. Identify support from CDC?!
Tanzania | 204 | ITP action | Support the production of skilled HR at central level (ToT) for patient monitoring at facility level (both skills and numbers) |  | lo
Tanzania | 208 | ITP action | Partner support for PSM-related systems strengthening activities discontinued from current partner support (storage, waste management, SOPs development, training, etc.) - technical support to identify critical gaps and partner(s) to support transition |  | what's the position regarding this action??????????? USG is not sponsoring this action! So is WHO sponsoring???
Tanzania | NI | SI |  | HIV case based surveillance | MOH wants it. A small group (WHO, CDC, UCSF, LSHTM)working on it. TWG still discussing and the CO will communicate what support will be required. IST and RO to review the tools. HQ to facilitate links with other partners.
Tanzania | NI | SI |  | HIV cascade analysis | The need to assist with TOT for cascade analysis. The CO will be working the details and communicate by April 2016. IST/RO/HQ ready to suppot both technically and financially | The proposal is to conduct cascade analysis training from 18 – 21 April, review patients monitoring system and develop M&E tools in the week before. | SIP provide $20,000 and AFRO was to provide another $20,000 to support the request. A consultant was proposed by SIP to support case-based surviellance. | This is linked to ITP action on patient monitoring.
Tanzania | NI | ART |  | Adaptation of the new 2015 WHO HIV guidelines | New guidelines based on WHO 2013 were launched in January 2016. Now looking at cost implications for moving to Treat All. In country discussions started and CO will communicate what ever require a TA
Tanzania | NI | PMTCT |  | Review of the eMTCT plan 2012-15 | MOH was a thourough situation analysis before development of new eMTCT plan TA will be required and CO will indicate | A follow up email was sent by Vindi on 3 June. George no longer works for WHO.
Tanzania | NI | Key populations |  | M & E for KP interventions in the country | KP programatic data analysis is being undertaken and Kp size estimates and mapping survey will be carried out. The country will share the survey protocol for comments
Uganda | 278 | ITP action | Address issues of quality of care and ensure retention strategy is in place to support scale up; TA support for country to project ART needs |  | Facilitate pre-testing of two more sections (Adult ART & eMTCT) of the comprehensive mentorship tool Organise a stakeholders retreat to compile a consolidated national clinical mentorship tool From TAC: Important for the national programme to have comprehensive grasp of what the challenges for providing quality care and retaining patients are. The deliverables focuses only on mentorship tools - which probably is to address health workers skills. Would suggets to include tools to strengthen retention in care and treatment adherence; harmonized use of indicators for monitoring quality of care at programme level; incorporate quality, inclduing retention and adherence interventions in health workers trainings.
Uganda | 279 | ITP action | Operational Support for patient monitoring system, building on existing system for PMTCT |  | Conduct a country assessment for Case Based Surveillance Adaptation global guideline to national context on HIV Case Based Surveillance Support development of costing tools for HIV Case Based Surveillance
Uganda | NI | Planning |  | Comprehensive Health Sector HIV Program review | WCO will send the concept paper for comments; WCO will also send formal request and TORs for TA that may be required
Uganda | NI | ART |  | Estimation of the Commodities/Financial need and gap based on a treat all model | HQ to work with partners to pilot the (Imperial College) estimation tool buiding on what PEPFAR through EquipNGOs is already doing
Uganda | NI | Testing |  | Revision and updating the National HIV Testing Guideline | IST/RO/HQ to review drafr guidelines
Uganda | NI | SI |  | HIV Cascade training including how to use routine PMTCT data for surveillance and HIV estimation | CO to prepare the concept note for the activity indicating the required amount and TA and share, HQ to share the guidelines on the subject;
Uganda | NI | PMTCT |  | Finalization of Integrated Mentorship tools | CO to share the draft tool for peer reviews
Uganda | NI | SI |  | Adaptation of the global strategy and guidelines for the prevention and control of viral hepatitis | Share the documents at various stages and HQ will support
Vietnam | NI | SI
Zimbabwe | NI | SI |  |  |  | As presented in the 2016 WCO HIV plan, Zimbabwe is planning to conduct a workshop to develop provincial and district HIV cascade using the 2015 data. This workshop is earmarked for the 1st week of February 2016. Requesting HQ participation in district cascade analysis workshop and financial support.
Zimbabwe | NI | Staffing |  |  |  | Funding to cover shortfall for HIV NPO in WCO
Zimbabwe | NI | ART |  |  |  | Zimbabwe is provisionally proposing a two day stakeholders’ consultative meeting (24- 25 May 2016) where the 2015 Guidelines are presented and the work of the Adaptation committee is shared and then consensus is reached on which guidelines to adopt and adapt. The MOH is requesting for a senior WHO technical Officer familiar with the guidelines to facilitate and document the proceedings of the 2 day workshop.
Zimbabwe | NI | SI |  | Development of sub-national cascade targets to enable monitoring and accountability at those levels. Finalization of revision of M&E and reporting tools | 7000 usd supported by HQ for SI cascade. Draft Report to be shared (next 3 weeks from 17 feb) Revision of M&E curriculum: Q2: ToRs to be shared. Need Consultant.
Zimbabwe | NI | ART |  | Adaptation of the 2015 ARV guidelines | Adaptation of 2015 WHO guidelines on going. Review of the HTS guidelines (end of May 2016) No need TA TA for senior person (2 days) HQ and AFRO to facilitate the validation process (before JHB)
Zimbabwe | NI | PMTCT |  | Pre-validation of eMTCT in preparation for validation | IST to provide tools and support
Zimbabwe | NI | Planning |  | Review of the HIV programmes as the initial step to developing a comprehensive HIV Health Sector Strategy | Consultancy to coordinate the review process